## wind
District Office | Field Office | Serial Number CACA | Applicant | Date Application Received and ROW Grant Issued | Acres | Megawatts (Mw) | Project Type | Geographic Area | Status of Application
Northern | Alturas | CACA 48119 | Invenergy LLC | 4/28/2006 11/7/2006 | 2888 |  | Wind: testing | Modoc County T4N, Rgs.12 &13E | AUTHORIZED; expires 12/2009
Northern | Alturas | CACA 49707 | Greenraven Wind LLC | 2008-02-08 | 17000 |  | Wind: testing | T34N, T35N, R13-15E | originally Eagle Lake
Northern | Alturas | N/A | EC&R West LLC (Airtricity, Inc.) | 2007-10-02 | 27995 |  | Wind: pending for testing | Modoc County, Madeline Peaks | PENDING
Northern | Alturas | N/A | Third Planet Windpower | 2008-07-25 | 18825 |  | Wind: pending for testing | B/t S Knobb & Likely Mtns T36N - 38N, R10-13E | PENDING
Northern | Alturas | N/A | Wind Power Partners LLC | 2007-04-23 | 3358 |  | Wind: pending for testing | Big Tableland Tps. 46&47N, R2E | PENDING
Northern | Alturas | CACA 50532 | Padoma Wind Power, NRG Inc. (East) | 2008-09-05 | 44614 |  | Wind: pending for testing | Mitchell Hill Area T35N-37N, R14E-17E | PENDING; area in ELFO, Surprise and Alturas. Alturas is lead FO.
Northern | Alturas | CACA 50531 | Padoma Wind Power, NRG Inc. (West) | 2008-09-23 | 31866 |  | Wind: pending for testing | Tule Mtn. Area T36N-38N, R11E-14E | PENDING; CRA sent 12/16/08
Central | Bakersfield | CACA 49112 | AES Seawest Inc. | 2007-04-20 | 200 |  | Wind: pending for testing | Kern County T31S, Rgs. 33,34,35E | Pending - Lands in both Ridgecrest and Bako FOs, RFO IS LEAD OFFICE
Central | Bakersfield | CACA 49459 | EC&R West LLC (Airtricity, Inc.) | 2007-10-22 | 26000 |  | Wind: pending for testing | Taft Kern County T3S, R21E | PENDING RMP completion
Central | Bakersfield | CACA 49460 | EC&R West LLC (Airtricity, Inc.) | 2007-09-26 | 2673 |  | Wind: pending for testing | Polonio Kern County R25S, R17E | PENDING RMP completion
Central | Bakersfield | CACA 49464 | EC&R West LLC (Airtricity, Inc.) | 2007-11-20 | 15286 |  | Wind: pending for testing | Lake Isabella Kern County T26S, R32E | PENDING RMP completion
CA Desert | Barstow | CACA 43088 | AES Seawest, Inc. | 6/20/2001 12/2004 | 4231 |  | Wind: testing | Daggett Ridges T8N, R1E &1W T9N, R1W | ROW testing issued. Expired 12/07. Renewal filed w/POD. Within DWMA Ord/Rodman, Monkey Flower ACEC.
CA Desert | Barstow | CACA 44975 | Granite Wind LLC | 11/18/2002 10/8/2003 | 1968 |  | Wind: testing | Granite Mtns T6N, R1 & 2W | ROW Amendment - 3yr extension for met study while POD is analysed & avian studies are conducted
CA Desert | Barstow | CACA 45097 | BP Alternative Energy | 1/8/2003 9/29/2003 | 2442 |  | Wind: testing | Sidewinder Mtn T6N, R2W | ROW testing renewed w/POD - expires 12/10 see CACA-48658 NOI Expected late 2008
CA Desert | Barstow | CACA 46803 | Horizon Wind Energy | 12/17/2004 2/9/2006 | 4479 |  | Wind: testing | Daggett T9N, R1W & 1E | ROW testing issued. Expires 12/09; requested to amend w/in DWMA rcvd CR Funds
CA Desert | Barstow | CACA 46804 | Horizon Wind Energy | 12/17/2004 2/9/2006 | 27808 |  | Wind: testing | Calico Mtns. T10N, R1&2E Private & public | ROW testing issued. Expires 12/09; requested to amend w/in DWMA rcvd CR Funds
CA Desert | Barstow | CACA 46805 | Horizon Wind Energy | 12/17/2004 2/9/2006 | 10073 |  | Wind: testing | Iron Mountain T8N, R3&4W | ROW testing issued. Expires 12/09; requested to amend w/in DWMA rcvd CR Funds
CA Desert | Barstow | CACA 46844 | Horizon Wind Energy | 12/22/2004 2/9/2006 | 720 |  | Wind: testing | Waterman Hills T10N, R2W | ROW testing issued. Expires 12/09; requested to amend w/in DWMA rcvd CR Funds
CA Desert | Barstow | CACA 46881 | AES Wind Generation, Inc. | 3/5/2005 8/26/2005 12/31/2011 | 2929 |  | Wind: testing | Sand Ridge | Grant expires 8/08. Amendment filed to add METs.filed. DWMA- Ord/Rodman, raptors, high tortoise concentration. Within Monkey Flower ACEC.
CA Desert | Barstow | CACA 47043 | FPL Energy | 2005-03-08 | 2449 |  | Wind: testing | West Fry Mtns. T5N, R2E | ROW testing issued. Expires 12/08. Renewal filed with POD. Pending decision. Partial w/in 29 Palms segregation; letter sent re: segregation, no response
CA Desert | Barstow | CACA 47100 | First Wind | 3/25/2004 6/15/2006 | 15837 |  | Wind: testing | Stoddard Mtns. T6N, R2W T7N, R1-4W | ROW testing issued. Expires 12/09
CA Desert | Barstow | CACA 47101 | First Wind | 3/25/2004 6/15/2006 | 6820 |  | Wind: testing | Granite Mtns. T5N, R1W & 1E | ROW testing issued. Expires 12/09; amended to move met tower
CA Desert | Barstow | CACA 47102 | First Wind | 3/25/2004 6/15/2006 | 10946 |  | Wind: testing | Fry Mountains T5N, R2 & 3E | ROW testing issued. Expires 12/09; w/in 29 Palms segregation area
CA Desert | Barstow | CACA 47103 | First Wind | 3/25/2004 6/15/2006 | 3458 |  | Wind: testing | Rodman Mtns. T6N, R3E | ROW testing issued. Expires 12/09; w/in 29 Palms segregation area
CA Desert | Barstow | CACA 47453 | (Iberdrola) Pacific Wind Development LLC | 8/17/2005 2/22/2006 | 5258 |  | Wind: testing | Waterman Hills T10N, R1&2W | ROW testing issued. Amendment approved 5/08 add met. Expires 12/09.
CA Desert | Barstow | CACA 47454 | (Iberdrola) Pacific Wind Development LLC | 8/17/2005 2/22/2006 | 2749 |  | Wind: testing | Elephant Mtns. R9N, R1W &1E | ROW testing issued. Amendment approved- add 1 met. Expires 12/09
CA Desert | Barstow | CACA 47455 | (Iberdrola) Pacific Wind Development LLC | 8/17/2005 2/22/2006 | 6623 |  | Wind: testing | Silurian Hills T15N, R8E T16N, R8E | ROW testing issued. Expires 12/09 Amendment approved- add 1 met.
CA Desert | Barstow | CACA 48254 | Sierra Renewables | 2006-07-24 | 1968 | 74 | Wind: developing | T5N, R10W & T5N, R20W | POD for CA 44975 received w/transmission. Cost recovery started. Proposed 28 turbines. Pending
CA Desert | Barstow | CACA 48471 | Power Parters SW (enXco) | 2006-10-10 | 10240 |  | Wind: pending for testing | Lone Mtn T6N, R1&2W | Application revision: Met locations & access. Draft EA rec'd 01/2007-5101/CRA set up Pending review/decision. Decision to deny Lone Mtn- within Milk Vetch ACEC. Advised appl. Pending decision to proceed with Troy Lake study.
CA Desert | Barstow | CACA 48472 | Power Parters SW (enXco) | 2006-10-10 | 10240 | 2 | Wind: pending for testing | Troy Lake T9N&10N, R4E | Application revision: Met locations & access. Draft EA rec'd 01/2007-5101/CRA set up Advised appl. pending decision to proceed with Troy Lake study.
CA Desert | Barstow | CACA 48629 | Oak Creek Energy | 2006-12-01 | 17290 |  | Wind: pending for testing | Black Lava T2N, R5E, T1N, R5E | Cost recovery finalized for met towers 08/12/08; partial w/in ACEC
CA Desert | Barstow | CACA 48658 | Orion BP Alernative Energy | 2006-12-15 | 2442 | 40-54 | Wind: developing | Sidewinder T8N, R6 & 7E | Revised POD received. 5101 setup. Work w/San Bernardino Co.Inital pre-NEPA mtg & Consultant SOW pending
CA Desert | Barstow | CACA 48689 | Renewergy, LLC | 2007-01-09 | 3920 |  | Wind: pending for testing | Black Lava Butte; T1N,R5E; T2N,R5E | Application complete Surveys and EA in progress Revision of access pending.
CA Desert | Barstow | CACA 48902 | West Fry Wind, LLC (FPL Energy) | 2007-03-29 | 3248 |  | Wind: developing | West Fry Mtns. T5N, R2E | POD for CACA-47043. NOI posted 5/08.Consultant selected. Initial scope done. Draft EIS in process. 35 turbines.
CA Desert | Barstow | CACA 49052 | GreenWing Energy (Alta Gas) | 2007-05-24 | 9546 |  | Wind: pending for testing | West Fry Mtns. T5N, R2E | Initial application incomplete. EA required. 5101 set up Biological & cultural surveys pending.
CA Desert | Barstow | CACA 49053 | GreenWing Energy (Alta Gas) | 2007-05-24 | 8553 |  | Wind: pending for testing | Mojave Valley between I-15 and I-40, east of Barstow Ghost Town T10N, R1E | Initial application incomplete. EA required. 5101 set up Biological & cultural surveys pending.
CA Desert | Barstow | CACA 49202 | Verde Resources, Inc (Western Wind). | 2007-06-07 | 3295 |  | Wind: pending for testing | N Stoddard Valley; T9N R1W & 2W | Initial application complete. EA required. 5101 set up Maps & met locations w/access rec'd 11/2007. Bilogical & cultural surveys underway. Awaiting draft EA
CA Desert | Barstow | CACA 49204 | Horizon Wind Energy | 2007-07-19 | 20811 |  | Wind: pending for testing | Stoddard/ Daggett | Initial application complete. EA required. 5101 set up; CR fund rcvd; Maps & met locations w/access rec'd 11/2007. Biological & cultural surveys underway. Awaiting draft EA; w/in DWMA
CA Desert | Barstow | CACA 49255 | EC&R West LLC (Airtricity, Inc.) | 2007-08-15 | 14080 |  | Wind: pending for testing | North Peak | Appl. Complete. EA received. Under revisions- will post for public comment period. 5101 setup.
CA Desert | Barstow | CACA 49575 | AES Wind Generation, Inc. | 2007-12-06 | 2930 | 84mW | Wind: pending for testing | Dagget Ridge Barstow T8N, R1E, R1W | App. Received. Draft POD received. On HOLD w/DWMA
CA Desert | Barstow | CACA 50032 | Debenham Energy | 2008-06-16 | 1508 |  | Wind: pending for testing | Ryan | Scoped, Cat VI fee determination
Central | Bishop | CACA 50218 | Padoma Wind Power, NRG Inc. | 2008-08-19 | 8950 |  | Wind: pending for testing | Black Lake Project 45 sq miles centered at Black Lake | Considering applying to Inyo NF too.
Northern | Eagle Lake | CACA 46727 | Plumas-Sierra Rural Electric | 10/1/2004 2/1/2006 | 10061 |  | Wind: testing | Lassen County Fort Sage Mtns. T25&26N, R17E T25N, R18E | AUTHORIZED Lands in both Eagle Lake and Carson City Fos. ELFO IS LEAD OFFICE; expires 12/2009
Northern | Eagle Lake | CACA 47238 | Horizon Wind Energy | 5/31/2005 5/19/2006 | 2222 |  | Wind: testing | Lassen County Antelope Mtn. T3N, 12&13E | AUTHORIZED; expires 12/2009
Northern | Eagle Lake | CACA 47239 | Horizon Wind Energy | 4/5/2005 11/17/2006 | 5497 |  | Wind: testing | Lassen & Plumas Co.s Beckwourth Pass T22N, R16E | AUTHORIZED; expires 12/2009
Northern | Eagle Lake | CACA 47240 | Horizon Wind Energy | 4/5/2006 6/7/2006 | 2560 |  | Wind: testing | Lassen County Observation Mtsn.T24N, R16 | AUTHORIZED; expires 12/2009
Northern | Eagle Lake | CACA 47241 | Horizon Wind Energy | 5/31/2005 5/30/2006 | 3837 |  | Wind: testing | Lassen County Snowstorm Mtn. T32N, 14&15E | AUTHORIZED; expires 12/2009
Northern | Eagle Lake | CACA 47242 | Invenergy LLC (Lassen Wind Generation LLC) | 4/6/2005 9/16/2005 | 19402 |  | Wind: testing | Lassen County Shaffer Mtn. T29&30N, R14E T29&30N, R15E T29N, R16E | AUTHORIZED Applicant submitted an amendment for additional testing acres on 12/26/06. Applicant submitted POD on 5/3/07. expires 12/2008
Northern | Eagle Lake | CACA 47957 | Distribution Generation Systems | 2/23/2006 11/01/2006 | 5542 |  | Wind: testing | Lassen County Snowstorm West T34N, R13E; T33&34N R14E | AUTHORIZED; expires 12/2009
Northern | Eagle Lake | CACA 48696 | Invenergy LLC | 11/7/2006 4/30/2007 | 93919 |  | Wind: testing | Lassen County Horse Lake Mtn. T33&34N, R11E T31&34N, R12E T31&34, R13E; T33&34N, R14E | AUTHORIZED: some met towers in type II, type I has 6 additional met towers; expires 12/2010
Northern | Eagle Lake | CACA 48921 | William Butler | 2007-03-29 | 640 |  | Wind: pending for testing | Skedaddle Mountains T29&30N, R16E | PENDING; deficiency letter sent 11/07
Northern | Eagle Lake | CACA 48927 | Horizon Wind Energy | 12/24/2006 10/18/2007 | 2.5 |  | Wind: testing | Lassen County Horse Lake Mtn. T33&34N, R11E T31&34N, R12E T31&34, R13E; T33&34N, R14E | AUTHORIZED Applicant submitted an amendment on 5/2/07 Applicant submitted POD on 3/6/07; expires 12/2010
Northern | Eagle Lake | CACA 49765 | BP Wind Energy North America | 2008-03-21 | 5937 |  | Wind: pending for testing | Lassen County Spanish Springs Pk Area T33N, R15E | Original ROW 45025 (Orion) - expired; PENDING; more info requested 3/31/08
CA Desert | El Centro | CACA 45248 | Pacific Wind (Iberdrola) | 2003-04-03 | 16354.5 |  | Wind: testing | McCain Valley, Eastern SD Cnty | ROW issued 9/15/04. Renewed 3 yrs 1/08 with submission of POD. 7/08 submitted apln to install add'l MET towers. Applicant advised that they must prepare EA. 08/08 relinquished 1262.62 acs.
CA Desert | El Centro | CACA 46618 | Clipper Windpower, Inc. | 2004-10-01 | 1318 |  | Wind: pending for testing | NECO Southeastern Imperial County T15S, R23E | Applicant was advised they need to prepare an EA due to staff workload. EA pending. Due diligence ltr will be issued.
CA Desert | El Centro | CACA 47518 | GreenHunter Wind Energy | 2005-09-01 | 6280 |  | Wind: pending for testing | Tocotillo W. Imperial County T16S/R9E T16S/R10E | FONSI and Decision Record Posted on website.
CA Desert | El Centro | CACA 47751 | Renewergy, LLC | 12/26/2005 1/23/2007 | 11187 |  | Wind: testing | Eastern Imperial County T12S/R20E T13S/R20E | Testing & monitoring ROW issued 1/2007; 1 met tower installed. Due diligence ltr pending. ROW expires 12/31/2010.
CA Desert | El Centro | CACA 48004 | Renewergy, LLC | 2006-04-26 | 3219 |  | Wind: pending for testing | Ocotillo, Western Imperial County T16S/R10E | EA nearing completion pending Native American consultation; Cultural lit search started
CA Desert | El Centro | CACA 48136 | Superior Renewable | 2006-06-06 | 187 |  | Wind: pending for testing | Ocotillo, Western Imperial County T16S/R19E | Applicant was advised they need to prepare an EA due to staff workload. EA pending. Due diligence ltr will be issued.
CA Desert | El Centro | CACA 48272 | Imperial Wind | 2006-07-31 | 1960 |  | Wind: pending for testing | Black Mountain Eastern Imperial County T12S/R20E T13S/R20E | Pending NEPA (DNA) and Native American consultation, as required by SHPO. (ROW (expired) previously authorized to another party for which EA was completed. Waiting Cultural Literature search.
CA Desert | El Centro | CACA 49698 | Pacific Wind (Iberdrola) | POD 12/26/07 | 9000 | 200 | Wind: developing | McCain Valley, Eastern SD Cnty | Cost recovery & POD ltr pending release of ROD for Eastern SD County RMP. Submitting modified POD by 1/1/09
Central | Hollister | CACA 48630 | Horizon Wind Energy | 11/24/2006 6/12/2007 | 1.1 |  | Wind: testing | Fresno & Kings Co. Kettleman Hills T22S, R17E | AUTHORIZED, Expires 5/31/10. Lands in both Bakersfield and Hollister Fos. HFO IS LEAD OFFICE
CA Desert | Needles | CACA 44988 | PPM Energy (Iberdrola) | 10/15/2002 8/7/2003 8/4/2006 | 2330 | 75 | Wind: testing | Mountain Pass T15N/R14E T151/2N/R14E | Cost recovery finalized for met towers 08/12/08. CX being done internally @ NFO
CA Desert | Needles | CACA 47539 | First Wind | 2005-08-11 | 10720 |  | Wind: pending for testing | Bristol Mountains T7N/R10E T7N/R11E | Pending - perfecting POD for outsource NEPA work. POD rec'd 9/20/04. CRA sent 7/2008
CA Desert | Needles | CACA 48287 | Renewergy, LLC | 2006-07-26 | 7760 |  | Wind: pending for testing | Bristol Mtns T7N/R10E T7N/R11E | Pending - cost recovery recv'd
CA Desert | Needles | CACA 48663 | Renewergy, LLC | 2006-08-02 | 2080 |  | Wind: pending for testing | Iron Mtn T1N/R17E, T1N/R18E | Pending. Rec'd $19k.
CA Desert | Needles | CACA 48664 | Renewergy, LLC | 2006-08-07 | 17320 |  | Wind: pending for testing | Homer Mtn T10N/R19E, T11N/R19E, T10N/R20E | Pending. Rec'd $19k.
CA Desert | Needles | CACA 48666 | Oak Creek Energy | 2006-08-06 | 7660 |  | Wind: pending for testing | Castle Mtns T13N/R17E, T14N/R17E, T15N/R17E, T14N.R18E, T15N/R18E | Pending - Joint project with Las Vegas FO Rec'd $15k.
CA Desert | Needles | CACA 48667 | Oak Creek Energy | 2006-08-11 | 25600 |  | Wind: pending for testing | South Ludlow T6N/R6E, T7N/R6E, T6N/R7E, T7N/R7E, T6N/R8E, T7N/R8E | Pending. Rec'd $15k
CA Desert | Needles | CACA 49433 | Padoma Wind Power, NRG Inc. | 2008-07-21 |  |  | Wind: pending for testing |  | CRA sent 05/08; recvd signed CRA 7/08; rcvd $26,369
CA Desert | Needles | CACA 50158 | Little Mountain Wind Power LLC | 2008-05-12 | 15000 |  | Wind: pending for testing | Bristol Lake T20N/R12E, T30N/R12E, T40N/R12E | Part is in Barstow FO boundary. Most in 29 Palms Segregation Area (14,100ac). Pending. Letter sent 11/17/08
CA Desert | Palm Springs | CACA 41695 | Mark Tech | 2002-12-27 | 74 | 5 | Wind: functioning or repower | T3S/R4E sec. 10 | will be closed
CA Desert | Palm Springs | CACA 46286 | AES/ SeaWest | 2005-01-24 | 265 | 75 | Wind: functioning or repower | T3S/R4E sec. 28 | NOA published 11/7/08; comment period closes 12/5/08; ROD by 12/12/08
CA Desert | Palm Springs | CACA 47660 NV80932 | Mesa | 10/6/2005 3/1/06 | 477 | 35 | Wind: functioning or repower | T3S/R3E, sec.4, 34 | ROW granted 3/1/06. Expires end of this year. 1,800 acres in NV. Waiting on BO; expected within 60 days.
CA Desert | Palm Springs | CACA 49487 | Sierra Renewables LLC | 2007-07-06 | 5300 |  | Wind: pending for testing | T6S/R10&11E | Within DWMA; current policy not allowed; review with new IM
CA Desert | Ridgecrest | CACA 13528 | Oak Creek Energy | 2002-04-03 | 160 | 20 | Wind: functioning or repower | Tehachapi Mountains | Repower; Right of Way grant issued; 11/7/08
CA Desert | Ridgecrest | CACA 44611 | Oak Creek Energy | 8/2/2002 5/27/2003 11/30/2005 | 1222 | 200 | Wind: testing | Mojave, Tehachapi | EA in staff review. Plan of development. Native American req's on met towers
CA Desert | Ridgecrest | CACA 45386 | Sierra Renewables LLC | 2002-12-11 | 8835 |  | Wind: pending for testing | Rose Valley/Little Lake | 29-day letter MOA for cost recovery Category VI; Consultation with Native American Tribe; follow Protocol with China Lake Military
CA Desert | Ridgecrest | CACA 46978 | Sean Roberts, Renewable Land LLC | 2004-07-01 | 467 |  | Wind: pending for testing | Mojave | Initiating CX for monitoring sites
CA Desert | Ridgecrest | CACA 47847 | Boulevard Associates | 2005-08-22 | 2678 |  | Wind: pending for testing | Tehachapi Mountains | EA in staff review. Split between Bakersfield and Ridgecrest offices; Native American Consultation req'd
CA Desert | Ridgecrest | CACA 47848 | Oak Creek Energy | 2006-01-11 | 6826 |  | Wind: pending for testing | Lucchese | 29-day letter MOA for cost recovery Calegory VI
CA Desert | Ridgecrest | CACA 48536 | Oak Creek Energy | 2006-07-25 | 1800 |  | Wind: pending for testing | Soledad Mountain Wind Project | 29-day letter MOA for cost recovery Category VI
CA Desert | Ridgecrest | CACA 48537 | Oak Creek Energy | 2006-06-25 | 19565 |  | Wind: pending for testing | Rand Mountain Wind Project | 29-day letter MOA for cost recovery Category VI
CA Desert | Ridgecrest | CACA 48948 | Renewergy, LLC | 2006-07-28 | 14209 |  | Wind: pending for testing | Rand Mountain area Laurel & El Paso Peaks | Initial application incomplete. EA required. 5101 set up Biological & cultural surveys pending.
CA Desert | Ridgecrest | CACA 49394 | Wind Power Partners | 2007-06-28 | 2080 |  | Wind: pending for testing | Base of Short Canyon | App. Received. Draft POD received. On HOLD w/DWMA
CA Desert | Ridgecrest | CACA 49547 | Competitive Power Ventures LLC | 2007-08-10 | 5000 |  | Wind: pending for testing | Bird Springs/ Inyokern | 29-day letter MOA for cost recovery Category VI
CA Desert | Ridgecrest | CACA 49577 | Power Parters SW (enXco) | 2007-08-10 | 1816 |  | Wind: pending for testing | Soledad area | 2nd in line behind Oak Creek (CACA 48536)
CA Desert | Ridgecrest | CACA 49581 | Sierra Renewables LLC | 2007-11-01 | 2554 |  | Wind: pending for testing | Inyokern/ Pearsonville | 29-day letter MOA for cost recovery Category VI. Southern portion of 45386.
CA Desert | Ridgecrest | CACA 50020 | Brewer Energy Co. | 2008-05-29 | 3200 |  | Met Towers | El Paso Mtns; W side of 395 | PENDING. 3 met towers; new appl.; Native Am. Consultation
CA Desert | Ridgecrest | CACA 50170 | Debenham Energy, LLC | 2008-07-27 | 16364 |  | Met Towers | E and W side of Haiwee Res and Hwy 395 | up to 8 met towers; 2 right away; new appl.; Native Am. Consultation
CA Desert | Ridgecrest | CACA 50319 | Debenham Energy, LLC | 2008-08-07 | 8096 |  | Met Towers | Summit Range; Crosses Hwy 395; (Searles Hills) | up to 8 met towers; 2 right away; new appl.; Native Am. Consultation
Northern | Surprise | CACA 48110 | Invenergy LLC | 7/17/2006 1/18/2007 | 4160 |  | Wind: testing | Lassen County T37N, R17E | AUTHORIZED; expires 12/2010
Northern | Surprise | N/A | Home Camp | 2006-03-06 |  |  | Wind: pending for testing | T42N, R18E, T43N, R18E | In NV. 5 towers proposed in recent amendment.
Northern | Surprise | N/A | Padoma Wind Power, NRG Inc. | 2008-09-13 | 25795 |  | Wind: pending for testing | Lassen and Washoe Counties, T36N - T38N | PENDING. 8 met towers proposed.
Northern | Surprise | N/A | Third Planet Windpower | 2008-09-16 | 6547 |  | Wind: pending for testing | b/t Buck and Little Hat Mtns; T37N R16E | PENDING. Selected withdrawn ROW area in amendment 11/19/08.
Northern | Surprise | N/A | Wild Madrone | 2008-05-27 | 343000 |  | Wind: pending for testing | Significant portions of T35 through T47N | PENDING
Northern | Ukiah | CACA 49639 | Alta Gas (GreenWing Energy) | 1/11/2008 5/15/2008 | 8157 |  | Wind: testing | Walker Ridge Lake, Colusa Ctys T14N, R5W T14&15N, R6W | AUTHORIZED; expires 12/2010
Northern | Ukiah | N/A | EC&R West LLC (Airtricity, Inc.) | 2007-10-03 | 3018 |  | Wind: pending for testing | Morgan Valley T12N, R5&6W | PENDING
|  |  |  | Total | 1197777.1
|  |  |  | Average | 12476.8448

## solar
District Office | Field Office | Serial Number CACA | Applicant | Date Application Received | Acres | Megawatts (Mw) | Project Type | Geographic Area | Status of Application
CA Desert | Barstow | CACA 47702 | Stirling Energy Systems, Inc. Solar Three | 2006-11-15 | 6779 | 914 | Solar: pending Stirling engine | Near Pisgah North of I-40 T's. 8, 9N., R5E | AFC & EIS pending with CEC as CEQA lead. Received completed amended application June 2007. Three separate projects. NOI Expected 12/08. Revised POD Received Oct 6, 2008.
CA Desert | Barstow | CACA 48563 | Stirling Energy Systems, Inc. Pilot site | 2006-11-15 | 15 | 1 | Solar: pending Stirling engine | Near Pisgah North of I-40 T's. 8N., R5E, Sec 18 | Application complete EA in progress (5101)
CA Desert | Barstow | CACA 48741 | Solar Investments VI LLC (G-S) | 2007-01-18 | 6400 | 800 | Solar: pending parabolic trough | (Baker) T. 14N., R.8E. | Application complete POD outline sent/ revisions? 5101 setup.
CA Desert | Barstow | CACA 48742 | Solar Investments, Inc. (G-S) | 2007-01-18 | 9600 | 1000 | Solar: pending parabolic trough | (Silurian Valley) T16N, R8E | Application complete POD outline sent/revisions?. Cost recovery letter to be sent-5101
CA Desert | Barstow | CACA 48743 | Solar Investments XI LLC (G-S) | 2007-01-18 | 10000 | 1200 | Solar: pending parabolic trough | (Salt Creek Hills) T18N, R7E & R8E | Application complete POD outline sent, revisons? EIS required 5101 paperwork pending to sent
CA Desert | Barstow | CACA 48818 | OptiSolar, Inc. | 2007-02-26 | 14400 | 1205 | Solar: pending parabolic trough | (Opal) T.2N, R9E &R10E | Received 5101 funds. w/in 29 Palms segregation area Received POD.
CA Desert | Barstow | CACA 48819 | OptiSolar, Inc. | 2007-02-26 | 15280 | 1000 | Solar: pending parabolic trough | (Desert Ruby) T3N, R5 & 6E; T4N, R5E | 5101 funds received. Partially w/in 29 Palms segregation area POD received.
CA Desert | Barstow | CACA 48875 | DPT Broadwell Lake LLC (Brightsource) | 2007-01-24 | 5130 | 500 | Solar: pending power tower | T'8N and 9N; R7E | Received 5101 funds. POD received.
CA Desert | Barstow | CACA 48941 | OptiSolar, Inc. | 2007-05-04 | 5120 | 585 | Solar: pending photovoltaic | (Desert Onyx) T11N, R3 & 4W | Sent 5101 letters CR Received (Proffer Established) Received POD
CA Desert | Barstow | CACA 49051 | FPL Energy, LLC (Blvd Assoc) | 2007-04-24 | 7680 | 1200 | Solar: pending parabolic trough | (Salt Creek) South of Silurian Dry Lake, East of Fort Irwin T16N, R8E & T15N, R7E | Received 5101 funds. Received POD.
CA Desert | Barstow | CACA 49357 | OptiSolar, Inc. | 2007-10-09 | 9520 | 500 | Solar: pending photovoltaic | (Jasper) T5N,R1E & T6N, R1W & T6N, R1W | Sent 5101 letters CR Received (Proffer Established) Received POD
CA Desert | Barstow | CACA 49361 | OptiSolar, Inc. | 2007-10-09 | 17920 | 500 | Solar: pending photovoltaic | (Amber) T4N,R3, R4E &R5E | Sent 5101 letters CR Received (Proffer Established) Rcvd POD; partially w/in 29 Palms segregation area
CA Desert | Barstow | CACA 49537 | Stirling Energy Systems, Inc. Solar One Phase 2 | 2007-03-14 | 3207 | 350 | Solar: pending Stirling engine | T.8&9N., R.5&6E | AFC & EIS pending with CEC as CEQA lead. Received 03/2007 - subdivided project from original Solar One. Revised POD Received Oct 6, 2008. Area in Pisgah ACEC Relinquished. Rcvd CR Funds
CA Desert | Barstow | CACA 49539 | Stirling Energy Systems, Inc. Solar One Phase 1 | 2007-03-14 | 4979 | 500 | Solar: pending Stirling engine | T.8&9N., R.6E | Received 3/2007 - subdivided project from original Solar One. Revised POD Received Oct 6, 2008. Rcvd CR funds
CA Desert | Barstow | CACA 49540 | Stirling Energy Systems, Inc. Solar Six | 2007-03-14 | 10044 | 1631 | Solar: pending Stirling engine | T.7&8N., R.7&8E | Received 3/2007 - subdivided project from original Solar One.Revised POD Received Oct 6, 2008.
CA Desert | Barstow | CACA 49561 | Chevron Energy Solutions Co. | 2007-12-07 | 367 | 40 | Solar: pending photovoltaic | T4N R2E. Secs; 19,20 | Application received POD revision pending. Received Oct 6, 2008.
CA Desert | Barstow | CACA 49584 | Caithness Soda Mtn, LLC (forner Solenergis) | 2007-12-18 | 1664 | 350 | Solar: pending photovoltaic | (Soda Mountain/Rasor) T12N, R7E &8E | Application received. Detailed POD received 9/16/08. review/approval of POD pending. EIS required. 5101 established
CA Desert | Barstow | CACA 49585 | Power Partners Southwest (EnxCo) | 2007-12-27 | 3840 | 1000 | Solar: pending parabolic trough | (Troy Lake) T8N, R4E, T9N, R4E | Application received. Revised map. POD revision rec. inadequate from outline. Follow up letter to be sent w/in 2 weeks
CA Desert | Barstow | CACA 49587 | Bull Frog Green Energy LLC | 2007-12-20 | 8999.4 | 300 | Solar: pending photovoltaic | (Bristol-Barstow) T.9N,R7E, SBBM | Appl. Received. Revise app rec. 9/10/08. POD needed. Outline sent. Only portion 1st in line
CA Desert | Barstow | CACA 49588 | Bull Frog Green Energy, LLC | 2007-12-20 | 11522.67 | 300 | Solar: pending photovoltaic | (Silver Mtn Vista) T7N, R3W, T6N, R4W &T8N, R4W | Application received. Revised App rec.9/10/08. POD needed. Outline sent.
Northern | Eagle Lake | CACA 49443 | DBK Solar Utilities of California | 2007-05-03 | 720 | 200 | Solar: pending other/ unknown technology | T29N, R16E | Application not complete. Second deviciency letter mailed 2/12/08. Allowed 60 days to respond. Sent POD letter on 8/21/08. Due 10/21.
CA Desert | El Centro | CACA 47740 | Stirling Energy Systems, Inc. (SES) Solar Two LLC | 2006-01-16 | 7000 | 750 | Solar: pending Stirling engine | Imperial County T16S Rgs. 10 and 11E | 5101 funds received. Joint EIS/IER with CEC as CEQA lead. AFC filed with CEC June 30, 2008. AFC/POD determined adequate under minimal criteria. NOI published 10/17/2008. Currently in discovery phase during which BLM/CPUC are requesting add'l info needed to initiate PSA/DEIS.
CA Desert | El Centro | CACA 48273 | BioRenewable Projects LLC | 2006-07-31 | 609 | 20 | Photovoltaic | Imperial County T. 11 S., R. 15 E., sec.6 | No monies or POD submitted yet. Cost recovery & POD ltr sent to applicant 08/14/08.
CA Desert | El Centro | CACA 49150 | SunPeak Solar | 2007-07-17 | 5587 | 500 | Solar: pending photovoltaic | Imperial County T13S, R12E | Received 5101 funds. POD received.
CA Desert | El Centro | CACA 49513 | SkyGen Solar LLC, c/o Invenergy | 2007-12-10 | 1040 | 50 | Solar: pending other/ unknown technology | Imperial County T12S, R11E, Sec 6 & 8 | 5101 monies received. POD letter & template sent to applicant 7/15/2008
CA Desert | El Centro | CACA 49613 | OptiSolar, Inc. | 2007-12-03 | 2560 | 500 | Solar: pending photovoltaic | Imperial County T13S, R9E; T12S, R9E | Inadequate POD submitted with application. Acreage needs to be refined. Working w/ applicant to identify issues. Cost Recovery and POD ltr sent to applicant on 7/30/08. CR funds rcvd; CRA not signed
CA Desert | El Centro | CACA 49615 | Pacific Solar Investments, Inc. (Iberdrola) | 2007-09-05 | 28000 | 1500 | Solar: pending parabolic trough | Imperial County Ts 14S & 15 S, Rs.19 & 20 E | Inadequate POD submitted with application. Acreage needs to be refined. Working w/applicant to identify issues. Cost Recovery & POD ltr sent to applicant 7/31/08. CR funds rcvd. $50k
CA Desert | El Centro | CACA 49884 | SolarReserve, LLC | 2008-04-24 | 4000 | 120 | Solar: pending power tower | Imperial County T16S, R17E, Sec 21, 22, 23, 26, 27, 28, 33, 34, 35 | 5101 monies rcvd. POD rcvd
CA Desert | El Centro | CACA 50013 | Power Partners Southwest LLC, c/o enXco | 2008-04-07 | 540 | 300 | Solar: pending parabolic trough | Imperial County T. 10 S., R. 14 E, sec.22, 26. | Partial rejection Sec 22 overlaps geothermal apln. 5101 monies rcvd. Cost recovery $50k & POD rcvd.
CA Desert | El Centro | CACA 50113 | Sempra Generation | 2008-07-21 | 11000 | 500 | Solar: pending photovoltaic | Imperial County T11/12S, R15/16E. | Cost recovery & POD ltr sent. CR fund and MOU rcvd; 2 secs BOR withdrawn lands. MOU signed
CA Desert | El Centro | CACA 50174 | LightSource Renewables LLC | 2008-08-11 | 3020.43 | 400 | Solar: pending parabolic trough | Imperial County T16/17S, R17/18 E., South of I-8, North of State Hwy 98. | CR Fund rcvd
CA Desert | Needles | CACA 48668 | Solar Partners Ivanpah SEGS (DPT Ivanpah LLC) | 2006-11-17 | 6720 | 400 | Solar: pending power tower | Ivanpah, S of the CA/NV line T16N/R14E, T17N/R14E | CACA 49502, 49503, 49504 Modified application twice to increase acreage. 1/4 cost recovery received ($42,280). Draft EIS expected Spring 2009; PSA due out 12/15/08
CA Desert | Needles | CACA 48669 | OptiSolar, Inc. | 2006-12-14 | 4160 | 380 | Solar: pending photovoltaic | Ivanpah Valley T17N/R14E | 1/4 cost recovery received ($40,767); POD letter sent 7/31/08. POD Rcv'd 9-30-08.
CA Desert | Needles | CACA 48758 | Cogentrix/Solar Investments VIII LLC | 2007-01-18 | 8000 | 320 | Solar: pending parabolic trough | Mesquite Hills T16N/R8E, T11N/R17E | 1/4 cost recovery rec'd ($199,047) 1 of 4 projects; Amended Decision w/ revised area due to partial conflict w CA 49004. POD Rcv'd 10-3-08
CA Desert | Needles | CACA 48759 | Cogentrix/Solar Investments XIII LLC | 2007-01-18 | 8960 | 1000 | Solar: pending parabolic trough | New York Mtns. T13N/R17E, T14N/R17E | 1/4 cost recovery received ($199,047) 2 of 4 projects; POD letter sent 7/23/08. Draft POD Rcv'd 9/26/08.
CA Desert | Needles | CACA 48760 | Cogentrix/Solar Investments I LLC | 2006-12-20 | 10880 | 1000 | Solar: pending parabolic trough | Amboy T6N/R11E, T7N/R11E | 1/4 cost recovery received ($199,047) 3 of 4 projects; POD letter sent 7/23/08. Draft POD Rcv'd 9-26-08;
CA Desert | Needles | CACA 48778 | Cogentrix/Solar Investments I LLC | 2007-03-23 | 5440 | 1000 | Solar: pending parabolic trough | Arrowhead T9N/R20E, T9N/R21E, T10N/R21E | Application accepted/rejected, in part 3/23/07. 1/4 cost recovery rec'd ($199,047) 4 of 4 projects; POD letter sent 7/23/08. Draft POD Rcv'd 9-26-08;
CA Desert | Needles | CACA 49002 | Leopold Companies, Inc. | 2007-04-02 | 37120 | 4100 | Solar: pending power tower | Ward Valley T1S/R19E, T1N/R19E, T2N/R19E, T1N/R20E, T2N/R20E | Sent 5101 letters CR Received (Proffer Established) Waiting for POD
CA Desert | Needles | CACA 49004 | Boulevard Associates, LLC | 2007-05-14 | 7200 | 1000 | Solar: pending parabolic trough | Mesquite Hills T10N/R8E, T11N/R8E,T11NR9E | Sent 5101 letters CR Received (Proffer Established) POD letter sent; letter for POD follow up being sent 11/21/08
CA Desert | Needles | CACA 49006 | Boulevard Associates, LLC | 2007-05-14 | 12160 | 1000 | Solar: pending parabolic trough | Killbeck T2N/R16E, T3N/R16E, T2N/R7E | Sent 5101 letters CR Received (Proffer Established) Received POD.
CA Desert | Needles | CACA 49008 | Boulevard Associates, LLC | 2007-05-14 | 35200 | 1000 | Solar: pending parabolic trough | Cadiz lake T1N/R15E, T2N/R15E, T1N/R16E, T1S/R16E, T2N/R16E | Sent 5101 letters CR Received (Proffer Established) Received POD.
CA Desert | Needles | CACA 49424 | Solel, Inc. | 2007-07-23 | 14080 | 600 | Solar: pending parabolic trough | Stedman T6N/R9E, T6N/R10E, T6N/R11E | Sent 5101 letters CR Received (Proffer Established) Received POD.
CA Desert | Needles | CACA 49429 | PG&E | 2007-09-11 | 18880 |  | Solar: technology neutral | Mesquite Lake T19N/R12E, T18N/R13E, T19N/R13E, T18N/R14E | Sent 5101 letters CR Received (Proffer Established) Revising to include transmission line; POD request letter being sent
CA Desert | Needles | CACA 49430 | Iberdrola Renewables | 2007-09-20 | 14720 |  | Solar: pending parabolic trough | Cadiz Lake T4N/R14E, T18N/R14E | CR Decision & letters sent 10/31/08. Discrepancy in legal (as of 11/24/08).
CA Desert | Needles | CACA 49431 | Boulevard Associates, LLC | 2007-09-21 | 9600 | 1000 | Solar: pending parabolic trough | Kellbaker Rd./ Amboy T6N/R12E, T7N/R12E, T6N/R13E | Received 5101 funds. Received POD.
CA Desert | Needles | CACA 49432 | PG&E | 2007-09-24 | 5120 | 800 | Solar: technology neutral | Cadiz/ Trilobite T5N/R13E, T5N/R14E | Received 5101 funds. Received POD. Awaiting next POD iteration for review ~ 12/15/08.
CA Desert | Needles | CACA 49812 | NextLight Renewable Power, LLC | 2008-03-24 | 12960 | 500 | Solar: pending parabolic trough | Iron Mountain T1N/R17E, T1N/R18E | CRA and CR Decision/POD letter sent
CA Desert | Needles | CACA 49813 | Iberdrola Renewables | 2008-04-01 | 12720 | 1000 | Solar: pending parabolic trough | Cadiz-East T4N/R15E, T4N/R16E | 1st in line; Iberdrola Renewables acquired Pacific Solar Investments (PSI)
CA Desert | Needles | CACA 49956 | Ewind Farm, Inc. | 2008-05-02 | 12640 | 800 | Solar: technology neutral | Iron Mountain, Clean Air Solar I T1N/R17E, T1N/R18E, T1S/R17E, T1S/R18E | Initial POD received 5/29/08
CA Desert | Needles | CACA 50116 | Ewind Farm, Inc. | 2008-05-26 | 13240 | 900 | Solar: technology neutral | Iron Mountain, Clean Air Solar II T1N/R17E, T1N/R18E, T1N/R19E | 1st in time
CA Desert | Needles | CACA 50117 | Ewind Farm, Inc. | 2008-05-27 | 21440 | 1700 | Solar: technology neutral | Iron Mountain, Clean Air Solar III T1N/R17E, T1N/R18E, T1S/R17E, T1S/R18E | 1st in time
CA Desert | Palm Springs | CACA 48649 | OptiSolar, Inc. (Desert Sunlight) | 2006-11-07 | 7040 | 350 | Solar: pending photovoltaic | Desert Center Area | Received 5101 funds. Received POD.
CA Desert | Palm Springs | CACA 48728 | Florida Power & Light | 2007-01-31 | 7773 | 250 | Solar: pending parabolic trough | Blythe Area, Eastern Riverside County | Received 5101 funds. Received POD. ROW in process for monitoring, water well drilling.
CA Desert | Palm Springs | CACA 48808 | Chuckwalla Solar LLC | 2006-09-14 | 4098 | 200 | Solar: pending photovoltaic | Desert Center area I | Received 5101 funds. NOI being sent out (for publication) in Federal Register 11/9/07
CA Desert | Palm Springs | CACA 48810 | Chevron Energy Solutions Co. #2 | 2007-02-15 | 3119 | 100 | Solar: pending parabolic trough | Desert Center area in Eastern RIVCO | Received 5101 funds. Received POD.
CA Desert | Palm Springs | CACA 48811 | Chevron Energy Solutions Co. #1 | 2007-02-15 | 3119 | 100 | Solar: pending parabolic trough | Blythe area in Eastern RIVCO | Received 5101 funds. Received POD.
CA Desert | Palm Springs | CACA 48880 | Florida Power & Light | 2007-01-31 | 4491 | 250 | Solar: pending parabolic trough | Blythe Area, Eastern Riverside County | NO 5101 funds received. Waiting POD
CA Desert | Palm Springs | CACA 49097 | Bullfrog Green Energy, LLC | 2007-06-13 | 6629 | 2500 | Solar: pending photovoltaic | Blythe Ca area S. of I-10 in Eastern RIVCO | 5101 funds received. POD received.
CA Desert | Palm Springs | CACA 49098 | OTB Power Holdings, Inc. | 2007-06-13 | 8742 | 1000 | Solar: pending photovoltaic | Blythe Ca area S. of I-10 in Eastern RIVCO | Sent 5101 letter. No 5101 funds Received. Wating for POD
CA Desert | Palm Springs | CACA 49397 | OptiSolar, Inc. (Quartzite) | 2007-09-28 | 3840 | 600 | Solar: pending photovoltaic | Blythe area in Eastern RIVCO | Sent 5101 letters CR Received (Proffer Established) Received POD.
CA Desert | Palm Springs | CACA 49486 | Solar Millennium, LLC | 2007-10-22 | 2753 | 500 | Solar: pending parabolic trough | Blythe area in Eastern RIVCO | No 5101 funds received. Waiting POD
CA Desert | Palm Springs | CACA 49488 | EnXco Development, Inc. | 2007-11-13 | 2070 | 300 | Solar: pending parabolic trough | Blythe area in Eastern RIVCO | Sent 5101 letters CR Received (Proffer Established) Received POD
CA Desert | Palm Springs | CACA 49489 | EnXco Development, Inc. | 2007-11-13 | 11603 | 300 | Solar: pending parabolic trough | Blythe area in Eastern RIVCO | Sent 5101 letters CR Received (Proffer Established) No POD rcvd
CA Desert | Palm Springs | CACA 49490 | EnXco Development, Inc. | 2007-11-13 | 12879 | 300 | Solar: pending parabolic trough | Blythe area in Eastern RIVCO | Sent 5101 letters CR Received (Proffer Established) Received POD.
CA Desert | Palm Springs | CACA 49491 | EnXco Development, Inc. | 2007-11-13 | 1071 | 300 | Solar: pending parabolic trough | Blythe area in Eastern RIVCO | Sent 5101 letters CR Received (Proffer Established) Received POD.
CA Desert | Palm Springs | CACA 49492 | EnXco Development, Inc. | 2007-11-13 | 1216 | 300 | Solar: pending parabolic trough | Blythe area in Eastern RIVCO | Sent 5101 letters CR Received (Proffer Established) Received POD.
CA Desert | Palm Springs | CACA 49493 | Solel Inc. | 2007-11-07 | 8775 | 500 | Solar: pending parabolic trough | Desert Center N. on Hwy 177 in Eastern RIVCO | Received 5101 funds. Received POD.
CA Desert | Palm Springs | CACA 49494 | Solel Inc. | 2004-11-07 | 7511 | 500 | Solar: pending parabolic trough | Desert Center N. on Hwy 177 in Eastern RIVCO | Received 5101 funds. Received POD.
CA Desert | Palm Springs | CACA 49702 | Bull Frog Green Energy, LLC | 2008-01-04 | 22912 | 2500 | Solar: pending photovoltaic | Blythe Ca area S. of I-10 in Eastern RIVCO | Received 5101 funds. Received POD.
CA Desert | Palm Springs | CACA 50379 | Lightsource Renewables, LLC | 2008-08-08 | 7920 | 550 | Solar: pending parabolic trough | Blythe Ca area S. of I-10 in Eastern RIVCO | CRA and MOU sent 11/14/08
CA Desert | Ridgecrest | CACA 48820 | Opti-solar, Inc. | 2007-02-13 | 5760 | 745 | Solar: pending photovoltaic | Mojave area near Hwy. 14 below Pin Tree Canyon, N. of Hwy. 58 | Sent 5101 letter. No 5101 funds Received. Received POD
CA Desert | Ridgecrest | CACA 49016 | Solar Millennium, LLC | 2007-03-23 | 11000 | 745 | Solar: pending parabolic trough | Near Ridgecrest City Limits off of Brown Rd. Hwy 395 | Received 5101 funds. Received POD.
CA Desert | Ridgecrest | CACA 49017 | Opti-solar, Inc. | 2007-04-03 | 6600 | 745 | Solar: pending photovoltaic | On the W side of Hwy 395 near Kramer Junction in the proximity of the current solar power plant development and the former Federal penitentiary. | Received 5101 funds. Letter sent to OptiSolar re: re-established application (11/13/08)
CA Desert | Ridgecrest | CACA 49511 | Opti-solar, Inc. | 2007-11-28 | 7182.5 | 600 | Solar: pending photovoltaic | On the E side of Ridgecrest along the boundary of China Lake Naval Weapons Center through Poison Canyon in the Hwy 178 corridor to Trona | Received 5101 funds. Letter sent to OptiSolar re: re-established application (11/13/08)
CA Desert | Ridgecrest | CACA 49960 | Corum Solar Array LLC | 2008-05-05 | 1200 | 100 | Solar: pending photovoltaic | Along Edwards AFB northern border below Hwy 58, within Kern County | Application just filed; POD not filed yet; Interconnect Study near completion; near SCE powerlines and substation.
CA Desert | El Centro | CACA 50515 | Blue Planet Power LLC | 2008-09-29 | 1281.51 | 250 | Solar: pending photovoltaic | Imperial County T10S, R15E, sec. 32; T11S, R15E, sec 4 | Cost recovery & POD ltr sent. 2nd in line for 2 secs.
|  |  |  | Total | 648368.51 | 51801